## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Closed / Due Date | Milestone | Labels | Functions/Screens
CORS, Helmet and rate-limiting hardening | Evidence: Gateway enables configured CORS, helmet() and ThrottlerGuard Verdict: Code-backed; runtime policy verification still belongs in release QA | 227 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/227 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Code-backed | CORS, Helmet and rate-limiting hardening
Structured logging and correlation propagation | Evidence: @wr/logger provides Pino logging, correlation middleware, TCP propagation and BullMQ patching Verdict: Code-backed; cross-service trace exercise is recommended | 224 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/224 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Code-backed | Structured logging and correlation propagation
Worker idempotency and retry safety | Evidence: CV parse/email skip completed work; reminders/email use stable job IDs; all 13 worker unit tests passed during documentation QA Verdict: Partially verified; retry/concurrency scenario was not run in this task | 223 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/223 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Partially verified | Worker idempotency and retry safety
Complete CV pipeline end-to-end verification | Evidence: scripts/e2e-role-flow.mjs uploads a CV but does not assert the complete parse -> embed -> search chain Verdict: Closure-evidence gap | 215 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/215 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Closure-evidence gap | Complete CV pipeline end-to-end verification
Authentication lifecycle end-to-end verification | Evidence: Role-flow script proves login only; auth unit specs exist, but no register/login/refresh/logout E2E artifact was found Verdict: Closure-evidence gap | 214 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/214 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Closure-evidence gap | Authentication lifecycle end-to-end verification
Full recruitment lifecycle end-to-end verification | Evidence: scripts/e2e-role-flow.mjs covers request -> approval -> plan -> posting -> CV/application -> interview -> decision -> offer response Verdict: Script present; environment-backed execution is still required | 213 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/213 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Partially verified | Full recruitment lifecycle end-to-end verification
Continuous integration and delivery pipeline | Evidence: No .github/workflows directory was found Verdict: Closure-evidence gap | 186 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/186 | Closed completed | vvtPhongdev |  | 2026-07-15 15:23 | Release Gate - 1.0-RC1 | Closure-evidence gap | Continuous integration and delivery pipeline
Accessibility audit - keyboard and color-independent status | Selected closed release evidence mapped to NFR-07, role screens | 228 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/228 | Closed |  |  | 2026-06-11 | Release Evidence | Closed evidence | NFR-07, role screens
Auto-trigger interview invitation email on schedule creation | Selected closed release evidence mapped to FR-13, FR-16, UC-49 | 226 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/226 | Closed |  |  | 2026-06-10 | Release Evidence | Closed evidence | FR-13, FR-16, UC-49
Extend audit logging to plans, interviews and CV screening | Selected closed release evidence mapped to NFR-03, AuditLog | 225 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/225 | Closed |  |  | 2026-06-10 | Release Evidence | Closed evidence | NFR-03, AuditLog
Health check endpoints for all microservices | Selected closed release evidence mapped to UC-61, NFR-06 | 222 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/222 | Closed |  |  | 2026-06-11 | Release Evidence | Closed evidence | UC-61, NFR-06
Global exception filter and standardized error responses | Selected closed release evidence mapped to NFR-01/NFR-05 | 221 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/221 | Closed |  |  | 2026-06-10 | Release Evidence | Closed evidence | NFR-01/NFR-05
Database seed script - required fixture set | Selected closed release evidence mapped to Installation and test data | 220 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/220 | Closed |  |  | 2026-06-17 | Release Evidence | Closed evidence | Installation and test data
Create packages/config validated environment schemas | Selected closed release evidence mapped to Configuration validation | 219 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/219 | Closed |  |  | 2026-06-11 | Release Evidence | Closed evidence | Configuration validation
Email templates - invitation, offer, rejection | Selected closed release evidence mapped to FR-16..18 | 218 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/218 | Closed |  |  | 2026-06-10 | Release Evidence | Closed evidence | FR-16..18
OfferLetterService - generation, review and send | Selected closed release evidence mapped to FR-17, UC-55/56 | 217 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/217 | Closed |  |  | 2026-06-09 | Release Evidence | Closed evidence | FR-17, UC-55/56
DOC-01 - Older docs use HR_MANAGER/HR_RECRUITER; implementation uses HR_LEADER | Older docs use HR_MANAGER/HR_RECRUITER; implementation uses HR_LEADER | DOC-01 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | Resolved in report set | Documentation team | 2026-07-15 |  | Documentation / Environment | Controlled report gap | MAP-01 terminology table; update legacy docs when touched
DOC-02 - Official lecturer, legal names and four student codes are absent from Git | Official lecturer, legal names and four student codes are absent from Git | DOC-02 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | External input required | Group lead | 2026-07-15 |  | Documentation / Environment | Controlled report gap | Group lead copies class-roster values before submission
DOC-03 - Original AI prompt/response screenshots are not stored in repository | Original AI prompt/response screenshots are not stored in repository | DOC-03 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | External evidence required | All members | 2026-07-15 |  | Documentation / Environment | Controlled report gap | Each member uploads their own course evidence
ENV-01 - Deployed web/API URL is not recorded | Deployed web/API URL is not recorded | ENV-01 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | Open | Deployment owner | 2026-07-15 |  | Documentation / Environment | Controlled report gap | Replace localhost placeholders after deployment
ENV-02 - Provider secrets are environment controlled | Provider secrets are environment controlled | ENV-02 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | Expected | Environment owner | 2026-07-15 |  | Documentation / Environment | Controlled report gap | Configure Supabase, Google, SMTP and optional Gemini without committing secrets
QA-01 - PlantUML and Excalidraw sources require render validation after edits | PlantUML and Excalidraw sources require render validation after edits | QA-01 | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md | Complete | Documentation QA | 2026-07-15 |  | Documentation / Environment | Controlled report gap | Eight PUML previews and the reviewed Excalidraw PNG are stored under reports/diagrams

## Status Summary
Issue Status Summary and Release Interpretation
Repository | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues
Baseline | 2026-07-15
Category | Count | Release interpretation
Open GitHub issues | 0 | GitHub API and repository tracker rechecked on 2026-07-15
Issues bulk-closed as completed | 7 | #186, #213, #214, #215, #223, #224 and #227 were closed by vvtPhongdev at 2026-07-15 15:23 UTC
Code-backed closures | 2 | #224 logging/correlation and #227 Gateway hardening have direct implementation evidence
Partially verified closures | 2 | #213 has an executable role-lifecycle script; #223 has worker guards/tests, but neither was executed end-to-end during documentation QA
Closure-evidence gaps | 3 | #214 full auth E2E, #215 full CV-pipeline E2E and #186 GitHub Actions workflow are not represented by complete artifacts in the reviewed tree
Release decision rule: 1.0-RC1 may be demonstrated in a controlled development environment. It is not promoted to production-ready until closure-evidence gaps are verified in a clean environment or explicitly risk-accepted by the project owner.

## Risk Matrix
Release Risk Matrix
Source | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template4_Issues%20Report.md
Release | 1.0-RC1
Risk | Likelihood | Impact | Related closure | Mitigation / exit criterion
Full workflow regression | Medium | Critical | #213 | Run the role lifecycle script against a clean seeded environment and retain its output
Auth/session regression | Medium | High | #214 | Add and pass register/login/refresh/logout/provider E2E
CV pipeline breakage | Medium | High | #215 | Add and pass upload/replace/parse/embed/search E2E with supported files
Duplicate queue side effects | Medium | High | #223 | Run retry and concurrency tests for every worker side effect
Hard-to-diagnose cross-service failures | Low | High | #224 | Exercise one correlation ID from Gateway through TCP and queue logs
API abuse/security headers | Low | High | #227 | Verify deployed CORS, Helmet headers and route-appropriate rate limits
Uncontrolled release quality | High | High | #186 | Add CI that runs format, lint, typecheck, build and tests on pull requests
Documentation drift | Medium | Medium | DOC-01 | Update MAP-01 and affected reports in the same change as code/schema