## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Setup CI/CD Pipeline & GitHub Actions Automation | Configure GitHub Actions workflow for automated linting, NestJS microservice builds, unit testing, and Docker Compose validation. | 186 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/186 | Closed | vvtPhongdev | 2026-06-05 09:00 | 2026-06-12 17:00 | Iter1 | Task, 3_Done | DevOps / CI
Recruitment Request & OverallPlan Approval Gate | Verify complete lifecycle of recruitment requests from Department Head creation to HR Queue review and Admin final approval/rejection. | 213 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/213 | Closed | vvtPhongdev | 2026-06-15 10:00 | 2026-06-25 17:00 | Iter2 | ReleaseGate, 3_Done | Request & Plan Governance
Authentication, JWT Lifecycle & Role Guard Security Gate | Implement and validate authentication flows including JWT access token generation, refresh token rotation, Google/Supabase OAuth, and role guards. | 214 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/214 | Closed | vvtPhongdev | 2026-06-08 08:30 | 2026-06-18 17:00 | Iter1 | ReleaseGate, 3_Done | User Login & Auth
CV Processing Pipeline, Vector Embedding & Talent Search Gate | Validate asynchronous CV file uploads, text parsing, 384-dim ONNX embedding generation, pgvector storage, and hybrid search matching. | 215 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/215 | Closed | LyHD-DE190075 | 2026-06-20 14:00 | 2026-07-05 17:00 | Iter3 | ReleaseGate, 3_Done | Candidate CV & Vector Search
Worker Queue Idempotency & BullMQ Task Retry Guards | Implement idempotency keys for CV embedding processing, deadline reminder jobs, and email dispatch to prevent duplicate executions. | 223 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/223 | Closed | vvtPhongdev | 2026-07-01 09:15 | 2026-07-10 17:00 | Iter3 | Task, 3_Done | Async Worker Processing
Structured Logging & Request Correlation ID Tracking | Integrate Pino logger across all NestJS microservices and append X-Correlation-ID to trace requests end-to-end. | 224 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/224 | Closed | vvtPhongdev | 2026-07-02 11:00 | 2026-07-08 17:00 | Iter3 | Task, 3_Done | System Operations
API Security Hardening: CORS, Helmet & Rate Limiting | Apply Security headers via Helmet, configure CORS origin whitelisting, and enforce rate-limiting guards on API Gateway. | 227 | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/227 | Closed | vvtPhongdev | 2026-07-03 13:00 | 2026-07-09 17:00 | Iter3 | Security, 3_Done | API Gateway
Zod-validated Environment Schema Validation | Create strongly typed environment config schemas using Zod for database URLs, JWT secrets, and microservice ports (T-101). | 343 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/343 | Closed | vvtPhongdev | 2026-07-05 08:00 | 2026-07-07 17:00 | Iter3 | Task, 3_Done | Configuration
Implement Microservice Health Check Endpoints | Implement /health endpoint for gateway, identity, recruiting, cv, interview, and worker services (T-104). | 344 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/344 | Closed | vvtPhongdev | 2026-07-05 10:30 | 2026-07-08 17:00 | Iter3 | Task, 3_Done | Operations / Health
Idempotency Guards for Recruitment Requests & Actions | Prevent duplicate submission of recruitment requests, offer responses, and interview schedules (T-105). | 352 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/352 | Closed | vvtPhongdev | 2026-07-06 14:00 | 2026-07-09 17:00 | Iter3 | Task, 3_Done | Request Workflow
Structured Logging & Pino Correlation ID Integration | Configure Pino logger and request correlation IDs across NestJS TCP microservices (T-106). | 353 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/353 | Closed | vvtPhongdev | 2026-07-07 09:00 | 2026-07-10 17:00 | Iter3 | Task, 3_Done | Logging Architecture
Resolve Pino DataCloneError in Worker Thread Pool | Fix worker thread serialization issue when passing pino logger context objects to BullMQ processors. | 356 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/356 | Closed | vvtPhongdev | 2026-07-07 16:00 | 2026-07-08 17:00 | Iter3 | Defect, 3_Done | Worker Processing
Extend Audit Logging for Plans, Interviews & CV Screening | Record granular audit log events for plan approval, interview panel evaluation, and screening decisions (T-107). | 316 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/316 | Closed | vvtPhongdev | 2026-07-08 11:00 | 2026-07-11 17:00 | Iter3 | Task, 3_Done | Audit & Compliance
HR Request Queue Assignment & Claim Workflow | Allow HR Leaders to claim, assign, return, or forward recruitment requests in the HR Queue (T-069). | 315 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/315 | Closed | dungnt585 | 2026-07-08 15:00 | 2026-07-12 17:00 | Iter2 | Task, 3_Done | HR Request Queue
Fix HR Request Queue & Status Badges | Correct status badge color mapping and request action buttons on the HR Leader Request Queue screen. | 317 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/317 | Closed | dungnt585 | 2026-07-09 08:00 | 2026-07-10 17:00 | Iter2 | Defect, 3_Done | HR Request Queue
Task Planner UI & Task Assignment Interface | Implement Task Planner calendar view and assignment modal for assigning campaign tasks to active HR staff. | 318 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/318 | Closed | dungnt585 | 2026-07-09 10:00 | 2026-07-11 17:00 | Iter2 | Feature, 3_Done | Task Planner
HR Talent Pool & Profile Drawer | Build Talent Pool candidate card grid, skill tags, and drawer preview for viewing parsed CV details. | 320 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/320 | Closed | hoanghoanghoainam083-cmyk | 2026-07-09 14:00 | 2026-07-12 17:00 | Iter3 | Feature, 3_Done | Talent Pool
AI Candidate Search & Vector Match Explanation UI | Implement AI Candidate Search interface with similarity percentage, skill match breakdown, and gap analysis. | 321 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/321 | Closed | vvtPhongdev | 2026-07-09 16:30 | 2026-07-13 17:00 | Iter3 | Feature, 3_Done | Candidate Search
Interview Schedule & Panel Selector Interface | Create interview scheduling modal with multi-panel selection, conflict detection, and online Meet link options. | 322 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/322 | Closed | vvtPhongdev | 2026-07-10 09:00 | 2026-07-13 17:00 | Iter3 | Feature, 3_Done | Interview Schedule
HR Recruitment Pipeline Report UI | Develop HR Pipeline Report dashboard showing conversion rates from screening to interview, offer, and hire. | 323 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/323 | Closed | hoanghoanghoainam083-cmyk | 2026-07-10 11:30 | 2026-07-14 17:00 | Iter3 | Feature, 3_Done | Pipeline Reports
HR Interview Results & Recommendation Submission | Implement panel scoring review, evaluation summary, and HR Leader final recommendation to Admin. | 324 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/324 | Closed | hoanghoanghoainam083-cmyk | 2026-07-10 14:00 | 2026-07-14 17:00 | Iter3 | Feature, 3_Done | Interview Results
HR System Notifications & Real-Time Alerts | Add real-time SSE notification listener, inbox dropdown, and read/unread status management for HR Manager. | 325 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/325 | Closed | hoanghoanghoainam083-cmyk | 2026-07-10 16:00 | 2026-07-15 17:00 | Iter3 | Feature, 3_Done | HR Notifications
Candidate Dashboard UI & Application Status Tracker | Build Candidate Portal dashboard showing active applications, screening status, and upcoming interview cards. | 326 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/326 | Closed | LyHD-DE190075 | 2026-07-11 08:30 | 2026-07-14 17:00 | Iter2 | Feature, 3_Done | Candidate Dashboard
Candidate Profile Management & Skills Editor | Create candidate profile page for editing personal details, technical skills, soft skills, and social links. | 327 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/327 | Closed | LyHD-DE190075 | 2026-07-11 10:30 | 2026-07-14 17:00 | Iter2 | Feature, 3_Done | Candidate Profile
Inbox Alerts & Notification History Modal | Build notification history modal and inbox alert list for candidates and department heads. | 328 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/328 | Closed | LyHD-DE190075 | 2026-07-11 13:00 | 2026-07-15 17:00 | Iter3 | Feature, 3_Done | Inbox Alerts
Candidate Upload CV & Parsing Status Interface | Develop drag-and-drop CV uploader with PDF/DOC/DOCX validation, parsing progress bar, and raw text preview. | 329 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/329 | Closed | LyHD-DE190075 | 2026-07-11 15:00 | 2026-07-15 17:00 | Iter3 | Feature, 3_Done | Candidate CV Upload
Candidate Interview Details & Confirmation Flow | Implement interview detail view for candidates to confirm attendance, request reschedule, or cancel. | 330 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/330 | Closed | LyHD-DE190075 | 2026-07-12 09:00 | 2026-07-15 17:00 | Iter3 | Feature, 3_Done | Candidate Interviews
Admin Dashboard & Overview Metrics | Connect Admin Dashboard to backend stats for total recruitment requests, active plans, and pending approvals. | 331 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/331 | Closed | duyhieu141 | 2026-07-12 11:00 | 2026-07-15 17:00 | Iter2 | Feature, 3_Done | Admin Dashboard
Admin Approval Queue & Request Review Modal | Build Admin Approval Queue for reviewing recruitment requests and overall plans with approval/rejection modal. | 332 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/332 | Closed | vvtPhongdev | 2026-07-12 13:30 | 2026-07-16 17:00 | Iter2 | Feature, 3_Done | Admin Approval Queue
Admin All Requests Search & Global Filtering | Implement global recruitment request search, department filtering, status filters, and timeline drawer for Admin. | 333 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/333 | Closed | duyhieu141 | 2026-07-12 15:30 | 2026-07-16 17:00 | Iter2 | Feature, 3_Done | Admin All Requests
Admin Final Hiring Decision & Offer Approval UI | Develop Admin Interview Results page for reviewing panel feedback and issuing final Hire/Reject decisions. | 334 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/334 | Closed | vvtPhongdev | 2026-07-13 08:30 | 2026-07-16 17:00 | Iter3 | Feature, 3_Done | Admin Interview Results
Admin User Management & Role Assignment | Build user management table, user creation form, role dropdown (Admin, HR, Dept Head, Candidate), and active status toggle. | 336 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/336 | Closed | duyhieu141 | 2026-07-13 11:00 | 2026-07-16 17:00 | Iter1 | Feature, 3_Done | Admin Users
Admin Organization & Department Settings UI | Implement Admin Settings interface for editing organization details, adding departments, and managing department heads. | 337 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/337 | Closed | duyhieu141 | 2026-07-13 14:00 | 2026-07-17 17:00 | Iter1 | Feature, 3_Done | Admin Settings
Annual Recruitment Reports & Export Capabilities | Create annual recruitment report graphs, time-to-hire charts, cost metrics, and CSV export functionality for Admin. | 338 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/338 | Closed | vvtPhongdev | 2026-07-13 16:00 | 2026-07-17 17:00 | Iter3 | Feature, 3_Done | Annual Reports
Department Recruitment Statistics & Metrics UI | Build department-level statistics view displaying request approval ratios, hiring velocity, and active campaign counts. | 339 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/339 | Closed | duyhieu141 | 2026-07-14 09:00 | 2026-07-17 17:00 | Iter3 | Feature, 3_Done | Department Statistics
Fix Authentication, Password Reset & Email Sending | Fix bug in login password verification, correct reset password link token expiration, and refine transactional email templates. | 341 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/341 | Closed | vvtPhongdev | 2026-07-14 11:30 | 2026-07-15 17:00 | Iter1 | Defect, 3_Done | User Login & Auth
Department Head Create Request Form & Priority Selector | Connect Department Head Create Request form to backend REST API with urgency priority selection and skill requirement inputs. | 349 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/349 | Closed | vvtPhongdev | 2026-07-14 14:00 | 2026-07-17 17:00 | Iter2 | Feature, 3_Done | Create Request
Department Head Requests Table & Status Filtering | Build Department Requests page with status tabs (Draft, Submitted, Approved, Rejected) and resubmission action. | 350 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/350 | Closed | vvtPhongdev | 2026-07-14 16:00 | 2026-07-17 17:00 | Iter2 | Feature, 3_Done | Department Requests
Connect Candidate Backend REST APIs | Implement candidate application submission, profile update, CV document retrieval, and interview list REST endpoints. | 358 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/358 | Closed | LyHD-DE190075 | 2026-07-15 09:00 | 2026-07-18 17:00 | Iter3 | Feature, 3_Done | Candidate Portal API
Connect Admin Dashboard, User & Requests APIs | Wire Admin portal screens to backend TCP microservices for user management, approval queue, and global request query. | 359 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/359 | Closed | duyhieu141 | 2026-07-15 11:00 | 2026-07-18 17:00 | Iter2 | Feature, 3_Done | Admin API Integration
Connect Department Head Pages to Backend REST APIs | Integrate Department Head Dashboard, Request Creation, Department Requests, and Team Settings with backend recruiting service. | 361 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/361 | Closed | vvtPhongdev | 2026-07-15 14:00 | 2026-07-18 17:00 | Iter2 | Feature, 3_Done | Dept Head API Integration
Connect HR Manager Pages to Backend REST APIs | Connect HR Request Queue, OverallPlan Workspace, Task Planner, Candidate Search, and Offer Letter modules to backend services. | 362 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/362 | Closed | vvtPhongdev | 2026-07-15 16:00 | 2026-07-18 17:00 | Iter3 | Feature, 3_Done | HR API Integration
Advanced Recruitment Workflow, ML & Storage Migrations | Update database schema with Prisma migrations, migrate file uploads to Supabase storage, and implement local ONNX E5-small-v1 embedding pipeline. | 366 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/366 | Closed | vvtPhongdev | 2026-07-16 09:00 | 2026-07-19 17:00 | Iter3 | Feature, 3_Done | Database & Storage Pipeline
Local Workflow Update & Improved CV Extraction Pipeline | Refine local candidate template parser, improve regex extraction rules, and update CV parsing fallback pipeline (T-108). | 373 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/373 | Closed | vvtPhongdev | 2026-07-17 10:00 | 2026-07-19 17:00 | Iter3 | Feature, 3_Done | CV Parse Pipeline
Split Panel Interview Feedback & Recommendation Flow | Split interview feedback submissions so panel evaluators score independently before HR Leader compiles final recommendation. | 375 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/375 | Closed | hoanghoanghoainam083-cmyk | 2026-07-17 14:00 | 2026-07-19 17:00 | Iter3 | Defect, 3_Done | Interview Feedback
Improve CV Upload Storage & AI Parsing Resilience | Enhance Supabase storage error handling, add Gemini API fallback keys, and optimize raw text extraction. | 376 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/376 | Closed | LyHD-DE190075 | 2026-07-17 16:00 | 2026-07-20 17:00 | Iter3 | Defect, 3_Done | CV Storage & Parsing
Connect Department Head Settings Team Members API | Fix Department Head settings page to fetch active team members and department headcount from identity service. | 377 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/377 | Closed | dungnt585 | 2026-07-18 09:00 | 2026-07-20 17:00 | Iter2 | Defect, 3_Done | Department Settings
Style Department Head Request Priority & Urgency Buttons | Refine UI button styles and color coding for request priority levels (Low, Medium, High, Urgent). | 380 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/380 | Closed | vvtPhongdev | 2026-07-18 11:30 | 2026-07-20 17:00 | Iter2 | Defect, 3_Done | Create Request
Refine Department Head Request Priority Workflow | Ensure high-priority recruitment requests trigger automated notification alerts to HR Leaders. | 381 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/381 | Closed | vvtPhongdev | 2026-07-18 14:00 | 2026-07-21 17:00 | Iter2 | Feature, 3_Done | Request Workflow
Update HR Task Assignment & Interview Result Flow | Fix task status transition bug when HR completes screening and updates interview evaluation results. | 382 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/382 | Closed | dungnt585 | 2026-07-18 16:00 | 2026-07-21 17:00 | Iter3 | Defect, 3_Done | Task Planner & Interviews
Vector AI Talent Search & Hybrid Matching Engine | Implement TalentSearchService combining pgvector 384-dim similarity, skillGraph distance, coverage score, and HR feedback weights. | 383 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/383 | Closed | vvtPhongdev | 2026-07-19 09:00 | 2026-07-21 17:00 | Iter3 | Feature, 3_Done | Vector AI Talent Search
Public Job Posting Dashboard & Candidate Application UI | Build public job posting board allowing unauthenticated candidates to view published jobs and submit applications. | 384 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/384 | Closed | hoanghoanghoainam083-cmyk | 2026-07-19 11:30 | 2026-07-21 17:00 | Iter3 | Feature, 3_Done | Job Posting Workspace
Identity Auth, Admin Calendar & Meeting Generation Flow | Integrate Google Calendar OAuth credential storage and auto-generate Google Meet video links for online interviews. | 385 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/385 | Closed | vvtPhongdev | 2026-07-19 14:00 | 2026-07-22 17:00 | Iter3 | Feature, 3_Done | Interview Calendar
Gemini API Key Fallback Slots Configuration | Add multiple Gemini API key slots in environment config to automatically rotate keys on rate limit errors. | 386 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/386 | Closed | vvtPhongdev | 2026-07-19 16:00 | 2026-07-22 17:00 | Iter3 | Task, 3_Done | AI CV Extractor
Allow Invited HR Interview Feedback Evidence Upload | Enable panel evaluators and invited HR members to upload supporting interview evaluation files and scoring notes. | 387 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/387 | Closed | hoanghoanghoainam083-cmyk | 2026-07-20 09:00 | 2026-07-22 17:00 | Iter3 | Feature, 3_Done | Interview Feedback
Complete Campaign Pipeline When Hiring Target Met | Automatically transition campaign status to COMPLETED and update task plans when final candidate accepts offer. | 389 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/389 | Closed | vvtPhongdev | 2026-07-20 11:30 | 2026-07-22 17:00 | Iter3 | Feature, 3_Done | Campaign Management
Refine Interview Attendance & Panel Evaluation Workflow | Add panel member attendance checkboxes and validation requiring at least two distinct active internal evaluators. | 390 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/390 | Closed | vvtPhongdev | 2026-07-20 14:00 | 2026-07-22 17:00 | Iter3 | Defect, 3_Done | Interview Schedule
Improve Candidate Search & Shortlist Workflow Integration | Integrate candidate search shortlist action with campaign application status, updating screening state and feedback log. | 391 | https://github.com/vvtPhongdev/SE20A05Group7RMS/pull/391 | Closed | vvtPhongdev | 2026-07-20 16:00 | 2026-07-23 17:00 | Iter3 | Feature, 3_Done | Candidate Search