## Project
RMS Total Project Tracking
Release 1.0-RC1 ¦ Baseline 2026-07-15 ¦ Product register mapped to RDS/SDS and iteration evidence
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Login, registration, OTP, password reset | Authentication | All | Account and session lifecycle, including Google/Supabase-backed flow | WS-3/WS-4 | Validation pending (#214) | Iter4 hardening | 2026-07-15 | Planned: Iter1 ¦ Trace: RDS 4.1 / SDS 4.1
2 | Admin Dashboard | Tracking | Admin | Approval, campaign and hiring overview | WS-2 | Done | Iter2 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.8 / SDS 4.8
3 | Admin Approval Queue | Request/Plan Governance | Admin | Approve, reject or request revision for requests/plans | WS-2/WS-5 | Validation pending (#213) | Iter3 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.2-4.3 / SDS 4.2-4.3
4 | Admin All Requests | Tracking | Admin | Global request search, status and timeline | WS-2 | Done | Iter3 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.8 / SDS 4.8
5 | Admin Interview Results | Hiring Decision | Admin | Review feedback and make final hire/reject decision | WS-1/WS-5 | Validation pending (#213) | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.6 / SDS 4.6
6 | Admin Users | Identity | Admin | Create/update users, role and active status | WS-4 | Done | Iter3 | 2026-07-15 | Planned: Iter1 ¦ Trace: RDS 4.1 / SDS 4.1
7 | Admin Settings | Organization | Admin | Organization and department configuration | WS-4 | Done | Iter3 | 2026-07-15 | Planned: Iter1 ¦ Trace: RDS 4.1 / SDS 4.1
8 | Annual Reports | Reporting | Admin | Annual metrics, time-to-hire and export | WS-2/WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.8 / SDS 4.8
9 | Department Statistics | Reporting | Admin | Department-level recruitment metrics | WS-2/WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.8 / SDS 4.8
10 | Department Dashboard | Tracking | Department Head | Own department requests, status and progress | WS-2 | Done | Iter2 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.8 / SDS 4.8
11 | Create Request | Recruitment Request | Department Head | Create draft with position, headcount, JD, skills, justification and urgency | WS-2/WS-1 | Validation pending (#213) | Iter4 alignment | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.2 / SDS 4.2
12 | Department Requests | Recruitment Request | Department Head | Edit/resubmit/delete allowed requests and view timeline | WS-2/WS-3 | Validation pending (#213) | Iter4 alignment | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.2 / SDS 4.2
13 | Department Interviews | Interview | Department Head | View invited interviews and attendance | WS-1/WS-2 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5 / SDS 4.5
14 | Department Feedback | Interview Result | Department Head | Submit panel scores and decision | WS-1/WS-5 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5 / SDS 4.6
15 | Department Settings | Organization | Department Head | View/update allowed department data and team | WS-1/WS-2 | Done | Iter3 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.1 / SDS 4.1
16 | HR Dashboard | Tracking | HR Leader | Queue, campaign, task and interview summary | WS-2 | Done | Iter3 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.8 / SDS 4.8
17 | HR Request Queue | Request Review | HR Leader | Assign/claim, edit, return and forward requests | WS-1/WS-3 | Validation pending (#213) | Iter4 alignment | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.2 / SDS 4.2
18 | Campaigns and Campaign Detail | Planning | HR Leader | Create, submit, resubmit and start OverallPlan | WS-1/WS-5 | Validation pending (#213) | Iter4 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.3 / SDS 4.3
19 | Task Planner | Planning | HR Leader | Create, assign and update dated campaign tasks | WS-1/WS-5 | Done | Iter4 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.3 / SDS 4.3
20 | Job Posting Workspace | Job Posting | HR Leader/Admin | Draft, upload media, publish and close posting | WS-4 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.4 / SDS 4.3
21 | Talent Pool | Candidate Management | HR Leader | Browse candidate profile and current CV | WS-1/WS-4 | Done | Iter3 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.4 / SDS 4.4
22 | Candidate Search | CV Search | HR Leader | Vector/hybrid search, shortlist and feedback | WS-4/WS-3 | Validation pending (#215) | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.4 / SDS 4.4
23 | Interview Schedule | Interview | HR Leader | Plan-locked schedule, panel validation, conflicts and invitations | WS-1/WS-5 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5 / SDS 4.5
24 | Interview Detail | Interview | HR Leader | Candidate, panel attendance, invitation and result details | WS-1/WS-2 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5 / SDS 4.5
25 | Interview Results | Interview Result | HR Leader | Own feedback plus final recommendation to Admin | WS-1/WS-5 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5-4.6 / SDS 4.6
26 | Pipeline Reports | Reporting | HR Leader | Pipeline overview and time-to-hire metrics | WS-4/WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.8 / SDS 4.8
27 | HR Notifications | Communications | HR Leader | In-app/SSE notification history and read state | WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.7 / SDS 4.7
28 | Candidate Dashboard/Profile | Candidate | Candidate | Maintain personal profile/avatar and view workflow summary | WS-2/WS-4 | Done | Iter3 | 2026-07-15 | Planned: Iter2 ¦ Trace: RDS 4.4 / SDS 4.4
29 | Candidate CV | CV Intake | Candidate | Upload, replace, delete and monitor PDF/DOC/DOCX processing | WS-1/WS-3 | Validation pending (#215) | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.4 / SDS 4.4
30 | Candidate Interviews | Interview | Candidate | View schedule and confirm/reschedule/cancel | WS-2/WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.5 / SDS 4.5
31 | Candidate Offers | Offer | Candidate | View offer and submit immutable accept/decline response | WS-5/WS-2 | Validation pending (#213) | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.6 / SDS 4.6
32 | Candidate Notifications | Communications | Candidate | View interview, status and offer messages | WS-2/WS-1 | Done | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 4.7 / SDS 4.7
33 | CV parse and embedding workers | Async Processing | System | Parse CV, structured extraction and vector generation | WS-1/WS-4 | Validation pending (#215, #223) | Iter4 | 2026-07-15 | Planned: Iter3 ¦ Trace: RDS 4.4 / SDS 4.4
34 | Task deadline reminders | Async Processing | System | Idempotent 24-hour/deadline reminder records and email jobs | WS-5 | Validation pending (#223) | Iter4 | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 5.3 / SDS 4.7
35 | Health and operational hardening | Operations | Admin/System | Aggregated health, exception handling, logging, rate limits and CI/CD | WS-1/WS-3 | Closure evidence review (#186, #224, #227) | Partial | 2026-07-15 | Planned: Iter4 ¦ Trace: RDS 5.5 / SDS 5.4

## Iter1
Iteration Tracking - Iteration 1
Planned scope and end-of-iteration result for Iteration 1
Columns B-D map the work item, identifier and implemented result from REP-01
Columns E-I record ownership, status, RDS/SDS trace and verification notes
# | Screen / Function | Work Item ID | Screen/Function Description | In Charge | Status | RDS / FR | SDS / UC | Notes
1 | Monorepo, shared packages and database baseline | I1-01 | Node/TypeScript/Turborepo structure established | WS-1 | Done | REP-02 / REP-01 | SDS 2-3 | Source trace: SDS 2-3
2 | Auth, JWT, refresh token and role guard | I1-02 | Identity TCP service and Gateway protection | WS-3/WS-4 | Validation pending | UC-01..UC-07, issue #214 | REP-03 mapped design | Source trace: UC-01..UC-07, issue #214
3 | Organization, department and user administration | I1-03 | Identity CRUD and role-scoped UI | WS-4 | Done | FR-01 | REP-03 mapped design | Source trace: FR-01
4 | RMS pivot requirements and workflow | I1-04 | Four-role workflow and plan-lock documented | WS-5 | Done | FR-02..FR-07 | REP-03 mapped design | Source trace: FR-02..FR-07
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Planned scope and end-of-iteration result for Iteration 2
Columns B-D map the work item, identifier and implemented result from REP-01
Columns E-I record ownership, status, RDS/SDS trace and verification notes
# | Screen / Function | Work Item ID | Screen/Function Description | In Charge | Status | RDS / FR | SDS / UC | Notes
1 | Department Head request lifecycle | I2-01 | Create/edit/submit/revise/track screens and services | WS-2/WS-3 | Validation pending | FR-02, issue #213 | REP-03 mapped design | Source trace: FR-02, issue #213
2 | HR review and Admin approval | I2-02 | Assign, return, forward, approve/reject/request-changes | WS-1/WS-5 | Validation pending | FR-03, issue #213 | REP-03 mapped design | Source trace: FR-03, issue #213
3 | OverallPlan and TaskPlan | I2-03 | Plan submit/approve/reject/resubmit/start and task operations | WS-1/WS-5 | Validation pending | FR-04..FR-07 | REP-03 mapped design | Source trace: FR-04..FR-07
4 | Role dashboards | I2-04 | Admin/HR/Department summary screens | WS-2 | Done | FR-20, FR-22 | REP-03 mapped design | Source trace: FR-20, FR-22
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Planned scope and end-of-iteration result for Iteration 3
Columns B-D map the work item, identifier and implemented result from REP-01
Columns E-I record ownership, status, RDS/SDS trace and verification notes
# | Screen / Function | Work Item ID | Screen/Function Description | In Charge | Status | RDS / FR | SDS / UC | Notes
1 | Candidate profile and CV lifecycle | I3-01 | Profile, upload, replace, delete and processing state | WS-1/WS-2/WS-3 | Validation pending | FR-08..FR-10, issue #215 | REP-03 mapped design | Source trace: FR-08..FR-10, issue #215
2 | Talent search and shortlist | I3-02 | Vector/hybrid search with feedback records | WS-4 | Validation pending | FR-11, issue #215 | REP-03 mapped design | Source trace: FR-11, issue #215
3 | Interview schedule and invitation | I3-03 | Plan-lock, panel, conflicts, notifications and email | WS-1/WS-5 | Done | FR-12, FR-13, FR-16 | REP-03 mapped design | Source trace: FR-12, FR-13, FR-16
4 | Panel feedback and recommendation | I3-04 | Per-evaluator feedback and HR recommendation | WS-1/WS-5 | Done | FR-14 | REP-03 mapped design | Source trace: FR-14
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Planned scope and end-of-iteration result for Iteration 4
Columns B-D map the work item, identifier and implemented result from REP-01
Columns E-I record ownership, status, RDS/SDS trace and verification notes
# | Screen / Function | Work Item ID | Screen/Function Description | In Charge | Status | RDS / FR | SDS / UC | Notes
1 | Admin final decision and offer response | I4-01 | Atomic hire/reject communication and candidate response | WS-5/WS-1 | Validation pending | FR-15, FR-17, FR-18; issue #213 | REP-03 mapped design | Source trace: FR-15, FR-17, FR-18; issue #213
2 | Notifications and reminders | I4-02 | SSE/in-app/email plus task deadline reminders | WS-1/WS-5 | Validation pending | FR-19; issue #223 | REP-03 mapped design | Source trace: FR-19; issue #223
3 | Annual, department and pipeline reports | I4-03 | Role-scoped tracking, metrics and export | WS-1/WS-4/WS-2 | Done | FR-20..FR-22 | REP-03 mapped design | Source trace: FR-20..FR-22
4 | Documentation and diagram set | I4-04 | Six reports, traceability, PUML and Excalidraw mapping | WS-3 + all | Done | REP-02 / REP-01 | REP-03 mapped design | Source trace: REP-00..REP-05
5 | Release hardening | I4-05 | Logging/rate-limit code present; GitHub Actions workflow absent | WS-1/WS-3 | Closure review | REP-02 / REP-01 | REP-03 mapped design | Source trace: Closed issues #186, #224, #227
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Release Gates
Release 1.0-RC1 Burndown and Evidence Gates
Closed gates | 7 | Total gates | 7
Source | https://github.com/vvtPhongdev/SE20A05Group7RMS/blob/main/reports/Template1_Project%20Tracking.md
Release gate | GitHub state | Evidence state | Issue URL
Full recruitment lifecycle E2E | #213 closed | Script present; clean-environment run not recorded | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/213
Auth E2E | #214 closed | Dedicated full-flow artifact not found | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/214
CV pipeline E2E | #215 closed | Upload covered; parse/embed/search assertions incomplete | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/215
Worker idempotency | #223 closed | Guards and unit specs present; retry/concurrency run pending | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/223
Structured logging/correlation | #224 closed | Pino/correlation implementation present | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/224
CORS/Helmet/rate limiting | #227 closed | Gateway implementation present | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/227
CI/CD pipeline | #186 closed | .github/workflows artifact not found | https://github.com/vvtPhongdev/SE20A05Group7RMS/issues/186
Release decision: all seven tracker items are closed, but incomplete verification evidence keeps the release label at 1.0-RC1 until clean-environment evidence is retained.